                  

**Reforming Foreign Languages in Academia in Montenegro**

**(Re-FLAME) – CBHE 609778**

**MONTHLY REPORT**

**August 2021**

Although the universities were on summer holidays, the preparation for the International Conference to be held in September continued. There was permanent communication among the team members on a daily basis regarding preparation of the LSP Conference. The tender procedure for literature was underway.

**WP3 – DEVELOPMENT: Procuring LSP textbooks and literature on applied linguistics and IT equipment**

3.1 Compiling a list of necessary LSP textbooks and literature on applied linguistics

* The tender for the procurement of literature for the University of Montenegro continued

**WP4 – DEVELOPMENT: FLT methodology**

4.7 Exchange FLT in HE experiences

– Planning and organization of the International Conference continued

- Reviews of the abstracts of the papers submitted for the Conference

**WP7 – DISSEMINATION AND EXPLOITATION**

7.2 Create a logo, develop and maintain a website

- The website was regularly maintained.

7.3 Advertise and promote the project

 - The FB and Twitter pages were maintained.

- Updated information on the summer school on the websites of all universities; posters that were put up and flyers distributed at all three universities

**WP8 – MANAGEMENT**

8.2 Perform overall management of the project

* Coordination of the activities related to the Summer School (applications, review of abstracts, provision of promotional material, preparation for printing the Book of Abstracts...)
* Regular communication of the project team regarding organisation of the LSP Conference to be held in September
* Coordination regarding deadlines for submission of abstracts for the LSP Conference
* Email communication with the EU partners and authors regading organisation of the LSP Conference

8.4 Write monthly progress reports

*-* The July report was adopted.

- The August report was written.

*Disclaimer*

*This project has been funded with support from the European Commission. This publication [communication] reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.*