I

**Reforming Foreign Languages in Academia in Montenegro**

**(Re-FLAME) – CBHE 609778**

**MONTHLY REPORT**

**15 July – 14 August**

Even though the ninth month coincided with the annual vacations, the work on several important tasks was continued. The first training was successfully completed on 21 July; the work on updating the syllabi was continued, and the work on writing nine LSP textbooks commenced.

**WP2 – DEVELOPMENT: Updating syllabi**

2.1 Write brief development

- The work on this task was continued (via email communication and Zoom).

**WP5 – DEVELOPMENT: LSP teaching materials**

5.1 Train FL teachers to write LSP teaching materials

- The first training ended on July 21.

5.2. Writing LSP textbooks.

- The work on writing nine LSP textbooks commenced. They are expected to be completed by March 2021.

**WP7 – DISSEMINATION AND EXPLOITATION**

7.2 Create a logo, develop and maintain a website

* The website was regularly maintained.

7.3. Advertise and promote the project

- The information on the successfully completed training session was disseminated and the certificates were made.

- The FB and Twitter pages were maintained.

**WP8 MANAGEMENT**

8.2 Perform overall management of the project

* The Italian partner received its payment.

8.4 Write monthly progress reports

*-* The eight monthly report was adopted.

- The ninth monthly report was written.

*Disclaimer*

*This project has been funded with support from the European Commission. This publication [communication] reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.*