Reforming Foreign Languages in Academia in Montenegro

(Re-FLAME) – CBHE 609778

QUALITY PROGRESS REPORT

DECEMBER 2019 – November 2020

The Annual Quality Progress Report encompasses a period of 12 months, from December 2019 till November 2020 that was affected significantly by the COVID - 19 pandemic. As per the Quality Management Guide, the task of the Re-FLAME Quality Board is to monitor and assess the quality of the activities conducted during all the significant stages of the project implementation.

The QPR 2020 will deal with the PREPARATION stage that was successfully completed unaffected by the force majeure effects imposed at the beginning of the DEVELOPMENT stage as well as the DEVELOPMENT stage of the project.

PREPARATION

KICK-OFF AND FOLLOW UP MEETINGS AND ACTIVITIES

Following the kick-off held in Nikšić on 12-13 December at which the Project activities were agreed upon with special emphasis on the first year of the project, the Project leader received positive feedback as regards the organization and implementation of the kick-off activities. A very intensive and productive email correspondence between the Project coordinator and Partners took place during the first month of the project, with a number of Montenegrin Re-Flame Team meetings organized as well as meetings with members of the university administration (rector, dean, vice-dean, financial and legal team (lawyer, accountant, public procurement officer), and the Erasmus+ Office.  Contact was also established with the project’s advisor assigned to the project in Brussels, Ms. Giulia Moro. Detailed information on all the meetings as well as attendance sheets completed are duly kept in the project records.

The IT member of the MNE team created a visually appealing Project logo, the Project website (www.reflame.ucg.ac.me ) was created (hosting provided by the  UoM)  and has been regularly updated with all the relevant info on the Project activities. The website has been regularly maintained. In addition, the website has been adapted for visually- and hearing-impaired persons, which is in line with the conclusions and recommendations reached at the kick-off meeting. This was not foreseen by the project application, so this is an extra task we have managed to accomplish.

All the relevant information, the attendance sheets, agenda, photo gallery, feedback and other relevant documentation were uploaded at the drive in a timely manner. The PC had a decisive managing role as she was in constant communication with all the team members in order to ensure a smooth implementation of all the planned activities in a timely, stress-free manner which contributed to the overall quality of the implementation.

STATUS QUO ANALYSIS

In the time period January-February as part of WP 1 an extensive, comprehensive and detailed status quo analysis was prepared and following a rigorous methodology the conclusions drawn which further testify to the importance and necessity of the project. A 70-page report was prepared by Deja Piletić and Petar Božović, the MNE team member available at www.reflame.ucg.ac.me.

Detailed research tools used, attendance sheets and minutes from internal meetings are kept in the project records under WP 1.1.

FL SYLLABI ASSESSMENT

A very intensive activity was centered around FL syllabi assessment. Most of the accredited syllabi have been collected at the UoM by Branka Živković (184 pages) and Zdravko Babić (120 pages). The UoM syllabi were evaluated by the UoM team members: Milica Vuković Stamatović, Vesna Bratić, Branka Živković and Deja Piletić. The syllabi were also gathered and evaluated at the UniMED and UDG. After the accredited syllabi were gathered and evaluated, the Project leader got invaluable suggestions by the Polish and Croatian partners to be implemented in the ensuing DEVELOPMENT stage. The documents are kept in the project records. All the necessary documentation is available at (www.reflame.ucg.ac.me). These are uploaded and updated in a timely manner.

SETTING-UP THE PROJECT OFFICE

The spacious facility has been allocated for the project office at the Faculty of Philology, Nikšić, furnishing is underway but the procedures have been seriously hampered by the health crisis and, we may say that this is the only challenge to be tackled with in the period extending beyond the preparation phase. However, as all other activities, including online teaching, the project-related activities have moved entirely into the virtual space of ZOOM virtual rooms. Therefore, this does not present such a serious problem as it might seem at first.

NB: A Management Guide, Quality Control Guide and a Dissemination Guide were developed and adopted by the relevant committees and boards. (WP 8) and are available at the Project websitewww.reflame.ucg.ac.me .

Monthly reports have all been developed detailing minutely all the activities and uploaded onto the website and the relevant Google archive in a timely manner by the PC.

DEVELOPMENT

For previously noted reasons, this stage of the project is under serious strain. The activities planned and agreed upon at the kick-off, such as study visits to partner institutions cannot be conducted.

This is why most of the activities are centered around the procurement of equipment which has also gone through some changes in terms of the items to be procured. In this respect, we would refer the QB members to the detailed Monthly report for February stating the reasons, procedures, meetings, communication, possible hindrances, etc.

WP 2 - DEVELOPMENT: Updating sillabi.

The work on this task was continued (via email and ZOOM communication). Important arrangements regarding this were made at the Steering Committee’s meeting. The Montenegrin partners got sufficient input to meet and produce a template for the new FL syllabi, which will then be revised into a final version with the help of the partners.

The Montenegrin partners have been working on the final version of the guidelines for updating the FL syllabi, which will be adopted in December 2020.

WP3 – DEVELOPMENT: procuring literature.

The list of necessary LSP textbooks and literature on applied linguistics was compiled by the Montenegrin partners and it was revised by the EU partners so that the tendering procedure could start.

The coordinator made changes to the financial plan and the plan of public procurement, which was administratively necessary after the project officer Giulia Moro had approved the changes requested by the three Montenegrin partners. The lists of literature to be procured were expanded and updated. The procurement is under way.

WP 4.1 - Study visits. Due to the pandemic study visits to the partner Universities in Croatia, Italy and Poland were not carried out.

WP5 – DEVELOPMENT: LSP teaching materials.

The meeting of the team in charge of coordinating the first training session "From texts to handouts and textbooks: Developing teaching materials for LSP" took place on 29 May 2020 via Zoom. The modalities, dates and the content of the training session were decided upon. A call for attending the seminar was disseminated and the teachers interested in the training applied. A Moodle course was set up for the training session. A series of additional mini-meetings was set up and intensive correspondence was exchanged as part of the preparation for the training session.

The first teacher training lasted from June 29 till July 21. It was organised online, by means of the Moodle platform run by the Faculty of Philology of the University of Montenegro, as well as Zoom and Microsoft Teams online meeting applications (run by the Italian partner), which ensured its continuity in real time, as well as interactivity and a crucially important exchange of experience amongst the colleagues. The instructors at the first training session were our partners from the University of Warsaw and the University for Foreigners of Perugia. The training was successfully completed by 31 Montenegrin LSP university teachers, who together created the teaching and learning materials which stand before you now, under the guidance and mentorship of the instructors.

The teaching materials collected here were produced as the seminar’s final assignments. Creating them meant applying the knowledge and skills acquired in the training session in the process of producing a well-structured module/unit in different languages for various specific purposes: science, arts, business, law, tourism, dentistry. They can be used as ready-made resources or as a pattern for creating own LSP teaching materials and writing LSP textbooks. We offer them for use under the Creative Commons licence and we hope that practitioners and students alike will find them useful in their LSP teaching or learning efforts. The Seminar proceedings will be published on-line and the procedure of getting the ISBN for this collection will be initiated.

The second FL teachers training session organized within the Erasmus+ Project Re-FLAME “From foreign language teaching methodology to syllabus design” was held from September, 21 till October, 2. The instructors at the second online workshop were our partners from the University of Zagreb and the University for Foreigners of Perugia. The course was aimed at training teaching staff members in general FLT teaching methodology and in state-of-the-art LSP teaching methodology. The course focused on practical methods of developing the four macro skills of reading, writing, speaking and listening and introduced techniques for teaching specialized vocabulary. The course course showed how to apply principles of language teaching and learning to lesson planning and syllabus design.

The second training was also organised online, by means of Zoom as well as the Moodle platform run by the Faculty of Philology of the University of Montenegro. It was attended by 31 LSP teachers from the three Montenegrin Universities.

Evaluation surveys were conducted after the first two training sessions. In both cases the majority of participants (about 80 %) stated they were very satisfied with trainings, materials, communication as well as IT platforms used for the trainings, and that they would definitely participate in the next trainings that will be organised within the Project Re-FLAME.

The certificates were issued for the participants of the two first training sessions.

The work on writing nine LSP textbooks commenced. They are expected to be completed by March 2021.

WP6 – QUALITY

The Quality Board prepared and adopted the Quality Progress Report for the period December 2019-April 2020.

A NEO monitoring visit was successfully conducted on 29 May 2020. It was attended by all the three Montenegrin partners. Neo monitoring feedback, which was largely positive, was received and replied to.

WP7 – DISSEMINATION AND EXPLOITATION

The website was regularly maintained.

The project poster was produced and put up in the Montenegrin partners’ institutions.

Information on the preparatory studies was disseminated on the website of the three Montenegrin institutions (including the UDG’s Instagram account).

The dean of the Faculty of Philology (UoM) was a guest in the morning show of the national public broadcasting company – RTCG. She took the opportunity to talk about the project, inter alia.

The information on the first and second training sessions was promoted on the websites of the three Montenegrin Universities, as well the Project’s and the Universities’ social network accounts.

The FB and Twitter pages were maintained.

WP8 MANAGEMENT

All bilateral agreements were signed despite the severe hindrances caused by the understaffing and impaired communication with the relevant office in the Rectorate during the pandemics. Between mid-February and the mid-March (just before the lockdown), the agreements with the two Montenegrin partners were signed and they submitted their requests for the first payment. The agreements were also signed with our foreign partners - the University of Zagreb and the University of Foreigners of Perugia. The agreement with the Polish university was re-revised. The final version of the Polish agreement was approved by both sides and signed.

All partners of the project submitted their first payment requests. All payments were made.

A meeting of the Steering Committee was conducted online on May 13, 2020. It was also attended by two NEO representatives. The year 1 schedule was revised and it was agreed that the first training session should be conducted online. The study visits were postponed.

The documentation for the tenders was completed again as the Law on Public Procurement was changed and completely new templates were published. The coordinator had an intensive communication with its procurement office as well as one live meeting – as the tendering procedure is supposed to be a joint one, there are some administrative hurdles that need to be worked out in line with new law, which does not foresee the possibility that a public institution carries out a tender for private institutions. The work on overcoming these hurdles in underway. Additionally, it is likely that a change to the Public Procurement Plan needs to be made – the current Plan is made based on the assumption that there the procurements will be individual; in order to make a joint procedure possible, it will need to be changed and adopted by the Management Board of the University of Montenegro.

All monthly reports  were written and adopted.

Disclaimer

The European Commission's support for the production of this publication does not constitute an endorsement of the contents, which reflect the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.